## Gantt Chart
GANTT CHART
TÊN ĐỀ TÀI |  | Xây dựng website quản lý chi tiêu cá nhân |  |  |  |  | LỚP | [6 empty] | CT23TTC11
NGƯỜI THỰC HIỆN |  | HOÀNG THIỆN |  |  |  |  | NGÀY | [6 empty] | 2025-08-04
STT | CÔNG VIỆC | NGƯỜI THỰC HIỆN | NGÀY BẮT ĐẦU | NGÀY KẾT THÚC | THỜI LƯỢNG | TỶ LỆ HOÀN THÀNH | GIAI ĐOẠN 1 |  |  |  |  | GIAI ĐOẠN 2 |  |  |  |  | GIAI ĐOẠN 3 | [14 empty] | GIAI ĐOẠN 4
[7 empty] | TUẦN 1 |  |  |  |  | TUẦN 2 |  |  |  |  | TUẦN 3 |  |  |  |  | TUẦN 4 |  |  |  |  | TUẦN 5 |  |  |  |  | TUẦN 6 |  |  |  |  | TUẦN 7
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Chuẩn bị báo cáo
1.1 | Chọn và đăng ký đề tài | me | 2025-08-04 | 2025-08-05 | 1 | 100% | bar: TUẦN 1 M to TUẦN 1 T
1.1.1 | Tạo tài khoản Github, đăng ký Collaborator | me | 2025-08-05 | 2025-08-06 | 1 | 100% | bar: TUẦN 1 T to TUẦN 1 W
1.2 | Thực hiện báo cáo Chương 1, 2, 3 | me | 2025-08-06 | 2025-08-07 | 1 | 100% | bar: TUẦN 1 W to TUẦN 1 R
1.3 | Khởi tạo dự án phần mềm | me | 2025-08-06 | 2025-08-07 | 1 | 100% | bar: TUẦN 1 W to TUẦN 1 R
1.4 | Commit tài liệu, báo cáo tiến độ lên Github | me | 2025-08-07 | 2025-08-08 | 1 | 100% | bar: TUẦN 1 R to TUẦN 1 F
2 | Phát triển sản phẩm - Backend
2.1 | Xây dựng các lược đồ quan hệ | me | 2025-08-11 | 2025-08-12 | 1 | 0% | bar: TUẦN 2 M to TUẦN 2 T
2.2 | Xây dựng cơ sở dữ liệu | me | 2025-08-12 | 2025-08-13 | 1 | 0% | bar: TUẦN 2 T to TUẦN 2 W
2.3 | Xây dựng các dịch vụ backend | me | 2025-08-13 | 2025-08-15 | 2 | 0% | bar: TUẦN 2 W to TUẦN 2 F
2.4 | Kiểm thử backend, commit báo cáo tiến độ lên Github | me | 2025-08-14 | 2025-08-15 | 1 | 0% | bar: TUẦN 2 R to TUẦN 2 F
3 | Phát triển sản phẩm - Frontend
3.1 | Xây dựng template chung | me | 2025-08-18 | 2025-08-20 | 2 | 0% | bar: TUẦN 3 M to TUẦN 3 W
3.2 | Xây dựng các trang tài khoản, đăng ký, đăng nhập | me | 2025-08-20 | 2025-08-22 | 2 | 0% | bar: TUẦN 3 W to TUẦN 3 F
3.3 | Xây dựng các trang danh mục | me | 2025-08-25 | 2025-08-27 | 2 | 0% | bar: TUẦN 4 M to TUẦN 4 W
3.4 | Xây dựng các trang nghiệp vụ | me | 2025-08-27 | 2025-08-29 | 2 | 0% | bar: TUẦN 4 W to TUẦN 4 F
3.5 | Nghỉ lễ |  | 2025-09-01 | 2025-09-02 | bar: TUẦN 5 M to TUẦN 5 T
3.5 | Kiểm thử frontend, commit báo cáo tiến độ | me | 2025-09-03 | 2025-09-05 | 2 | 0% | bar: TUẦN 5 W to TUẦN 5 F
4 | Chạy thử sản phẩm - Hoàn chỉnh báo cáo
4.1 | Kiểm thử toàn hệ thống | me | 2025-09-08 | 2025-09-10 | 2 | 0% | bar: TUẦN 6 M to TUẦN 6 W
4.2 | Hoàn chỉnh báo cáo | me | 2025-09-10 | 2025-09-12 | 2 | 0% | bar: TUẦN 6 W to TUẦN 6 F
4.3 | Commit tài liệu, báo cáo tiến độ lên Github | me | 2025-09-11 | 2025-09-12 | 1 | 0% | bar: TUẦN 6 R to TUẦN 6 F
4.4 | Chuyển giao sản phẩm | me | 2025-09-15 | 2025-09-16 | 1 | 0% | bar: TUẦN 7 M to TUẦN 7 T
4.5 | Nhận phản hồi và điều chỉnh | me | 2025-09-16 | 2025-09-19 | 3 | 0% | bar: TUẦN 7 T to TUẦN 7 F

## Project Tracking (hidden)
PROJECT TRACKING | [12 empty] | STATUS KEY | PRIORITY KEY
[13 empty] | On Hold | Low
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [Company's name] |  |  |  |  | Not Yet Started | Medium
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | 2025-08-04 |  |  |  |  | In Progress | High
Complete
PROJECT DETAILS | [7 empty] | DELIVERABLES |  | COST/HOURS
STATUS | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | FIXED COST | ESTIMATED HOURS | ACTUAL HOURS
PHASE 1 - CHUẨN BỊ TÀI NGUYÊN | [8 empty] | 0% | 0 | 0 | 0
In Progress | High | 2025-08-04 | 2025-08-05 | 1 | Task |  | Chọn đề tài và đăng ký với nhà trường |  | 0%
Not Yet Started | Medium | 2025-08-05 | 2025-08-05 | 0 | Task |  | Tạo tài khoản Github. Thêm giáo viên vào danh sách Collaborator |  | 0%
Not Yet Started | Medium | 2025-08-05 | 2025-08-05 | 0 | Task |  | Xây dựng khung tài liệu (những mẫu tài liệu nào được sử dụng) |  | 0%
PHASE 2 - XÂY DỰNG ỨNG DỤNG | [8 empty] | 0% | 0 | 0 | 0
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Details of task here |  | 0%
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Details of task here |  | 0%
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Details of task here |  | 0%
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Details of task here |  | 0%
PHASE 3 - HOÀN THIỆN BÁO CÁO | [8 empty] | 0% | 0 | 0 | 0
On Hold | High | 2018-09-09 | 2018-09-10 | 1 | Task |  | Details of task here |  | 0%
Not Yet Started | Low | 2018-09-10 | 2018-09-14 | 4 | Task |  | Details of task here |  | 0%
In Progress | Medium | 2018-09-11 | 2018-09-20 | 9 | Task |  | Details of task here |  | 0%
Complete | Medium | 2018-09-12 | 2018-09-20 | 8 | Task |  | Details of task here |  | 0%

## Project Timeline (hidden)
PROJECT TIMELINE TEMPLATE |  |  |  | Smartsheet Tip ➜ | [5 empty] | This is a modified form of a Gantt chart which focuses on creating a project schedule that is broken down into stages.
PROJECT TITLE |  | [Project's title] |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  | DATE | [6 empty] | 2018-03-12
PHASE |  |  | DETAILS | Q1 | [10 empty] | Q2 |  |  |  | Q3 |  |  |  | Q4
|  |  |  | JAN |  |  |  |  | FEB |  |  |  | MAR |  | APR |  | MAY | JUN | JUL |  | AUG | SEP | OCT | NOV | DEC
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Project Conception and Initiation |  | - Project Charter | JAN 16: Project Charter | [7 empty] | PROJECT END
|  |  | - Plan Review | FEB 13: Plan Review
|  |  | - Initiation | [10 empty] | Initiation
2 | Project Definition and Planning |  | - Scope and Goal Setting | [11 empty] | Scope and Goal Setting
|  |  | - Budget | [12 empty] | Budget
- Work Breakdown Schedule
- Gantt Chart
- Communication Plan
- Risk Management
3 | Project Launch & Execution |  | - Status and Tracking
- KPIs
- Quality
- Forecasts
4 | Project Performance & Control |  | - Objective Execution
- Quality Deliverables
- Effort and Cost Tracking
- Performance
5 | Project Close |  | - Postmortem
- Project Punchlist
- Report